## 🎯 Master Dashboard
AUTOERA AI — COMPLETE EXECUTION OPERATING SYSTEM ¦ Idea to IPO
COMPANY HEALTH — LIVE INDICATORS
Current Stage | MRR Target M12 | Burn Rate | Runway | Next Milestone | IPO Target
Pre-Seed / MVP | ₹8 Lakhs | ₹7.2L/month | 22 months | 50 paying dealers | Year 10–12
19-STAGE MASTER ROADMAP OVERVIEW
Stage | Name | Core Activity | Exit Criteria | Timing | Status | Priority
S0 | Founder Preparation | Mindset, registration, legal, banking, accounting | PMF signal unknown | Week 1–4 | 🔴 Active | 🔥 NOW
S1 | Market Research | TAM/SAM/SOM, competitor analysis, pricing research | 10 dealer interviews | Week 5–6 | ⚪ Pending | 🔥 NOW
S2 | Customer Discovery | 50 dealer conversations, pain validation | Pain confirmed by 80% | Week 7–10 | ⚪ Pending | 🔥 NOW
S3 | Problem Validation | Specific feature requirements locked | 5 LOIs signed | Week 11–12 | ⚪ Pending | ⚡ NEXT
S4 | MVP Planning | PRD, wireframes, tech stack, sprint plan | Sprint 1 ready | Month 3 | ⚪ Pending | ⚡ NEXT
S5 | MVP Development | ServicePulse + Tamil Voice Agent built | Working demo | Month 3–5 | ⚪ Pending | ⚡ NEXT
S6 | Pilot Customers | 5 dealers using product daily (no charge) | 20+ job cards/dealer | Month 4–6 | ⚪ Pending | 📋 PLANNED
S7 | First Revenue | First ₹ collected — minimum 5 paying dealers | ₹60K MRR | Month 5–7 | ⚪ Pending | 📋 PLANNED
S8 | Product-Market Fit | NPS>40, churn<3%, 3 referrals received | 30 dealers paying | Month 9–12 | ⚪ Pending | 📋 PLANNED
S9 | Scale Chennai | 50 dealers, ₹8L MRR, cluster dominance | 50 paying dealers | Month 12–15 | ⚪ Pending | 📋 PLANNED
S10 | Scale Tamil Nadu | 200 dealers across TN, Series A closed | ₹30L MRR | Month 15–24 | ⚪ Pending | 📋 PLANNED
S11 | Scale India | 800 dealers nationally | ₹1.2Cr MRR | Year 2–3 | ⚪ Pending | 📋 PLANNED
S12 | OEM Partnerships | 1 signed OEM network contract | ₹5Cr ARR | Year 2–3 | ⚪ Pending | 📋 PLANNED
S13 | Series A | ₹15–25Cr raised at ₹80–120Cr pre-money | Series A closed | Month 20–24 | ⚪ Pending | 📋 PLANNED
S14 | International | UAE + SEA pilot, ₹100Cr ARR | ₹100Cr ARR | Year 4–5 | ⚪ Pending | 📋 PLANNED
S15 | Series B | ₹75–150Cr raised | 2,000 dealers | Year 5–6 | ⚪ Pending | 📋 PLANNED
S16 | Category Leadership | #1 Automotive AI globally by ARR | ₹500Cr ARR | Year 7–8 | ⚪ Pending | 📋 PLANNED
S17 | IPO Readiness | SEBI compliance, audits, governance | ₹1,000Cr ARR | Year 9–10 | ⚪ Pending | 📋 PLANNED
S18 | IPO | Listed on NSE or NASDAQ | Market cap ₹10,000Cr+ | Year 10–12 | ⚪ Pending | 📋 PLANNED

## 📅 10-Year Roadmap
AUTOERA AI — 10-YEAR EXECUTION ROADMAP ¦ 2026–2036
Year | Revenue | Customers | Employees | Stage | Key Product | AI Milestone | Funding | Marketing | Sales | Structure
Year 1 (2026) | ₹0 → ₹1.2Cr | 0 → 80 dealers | 1 → 12 | MVP + PMF | ServicePulse + Tamil Voice Agent | Tamil NLP v1, WhatsApp agent | ₹2Cr angel/pre-seed | Founder-led, FADA events, WhatsApp demos | Founder + 1 BD (M4) | Flat — 3 engineers + domain expert
Year 2 (2027) | ₹1.2Cr → ₹10Cr | 80 → 400 dealers | 12 → 35 | Scale TN + Series A | InsureGuard + FinanceFlow + Analytics Hub | Multi-agent orchestration, Tamil ASR v2 | ₹15–25Cr Series A | Content + LinkedIn + FADA TN partnership | VP Sales + 5 BD reps | Functional: Engg/Sales/CS/Product
Year 3 (2028) | ₹10Cr → ₹40Cr | 400 → 1,200 dealers | 35 → 90 | Scale India + OEM | FleetIQ + EVIntel + OEM Dashboard | Predictive maintenance ML v1, OBD-II pipeline | Series A deployed | National brand + PR + case studies | Regional sales (South + West) | Divisional: SMB/Enterprise/OEM
Year 4 (2029) | ₹40Cr → ₹100Cr | 1,200 → 2,500 dealers | 90 → 180 | National dominance | Customer App v2 + API platform | EV degradation model, voice AI v3 | Series B raise begins | National advertising + OEM co-brand | Enterprise team + OEM BD | Full C-suite + board expansion
Year 5 (2030) | ₹100Cr → ₹250Cr | 2,500 → 5,000 dealers | 180 → 350 | Series B + International | Global localisation (UAE Arabic, Bahasa) | Cross-market AI model transfer | ₹75–150Cr Series B | UAE + SEA market entry | Country teams: UAE + Singapore | Global HQ (Singapore) + India HQ (Chennai)
Year 6 (2031) | ₹250Cr → ₹500Cr | 5,000 → 9,000 dealers | 350 → 600 | Platform + Ecosystem | Developer API marketplace + third-party apps | Autonomous dealer operations AI | Series C or profitability | Global category leadership PR | Dedicated enterprise + platform sales | Platform org + ecosystem team
Year 7 (2032) | ₹500Cr → ₹800Cr | 9,000 → 14,000 dealers | 600 → 900 | Pre-IPO scale | AutoEra AI v3 — full automotive OS | Real-time fleet + EV autonomous management | Pre-IPO secondary round possible | Brand = category. AutoEra = Automotive AI globally | Africa + Latin America pilots | Public-company-grade governance
Year 8 (2033) | ₹800Cr → ₹1,200Cr | 14,000 → 20,000 dealers | 900 → 1,400 | IPO readiness | Full automotive ecosystem platform | AI agents replacing 50% of dealer workforce tasks | IPO roadshow preparation | Investor relations function built | Pan-Asia + Middle East coverage | SEBI/SEC compliant governance
Year 9 (2034) | ₹1,200Cr → ₹1,800Cr | 20,000+ dealers | 1,400 → 2,000 | IPO | Mature SaaS + AI platform | Proprietary foundation model for automotive | NSE or NASDAQ IPO | IPO roadshow + institutional investor relations | Post-IPO sales acceleration | Public company — SEBI LODR compliant
Year 10 (2035) | ₹1,800Cr → ₹2,500Cr+ | 30,000+ globally | 2,000 → 3,000 | Post-IPO growth | Global automotive AI standard | Industry-specific AGI layer for automotive | Public market capital | Global brand — The Salesforce of Automotive | Global enterprise + platform | Multi-geography public company

## 📆 120-Month Plan
AUTOERA AI — 120-MONTH EXECUTION PLAN ¦ Monthly Milestones & Deliverables
Month | Period | Primary Objectives | Key Deliverables | Expected Outcome | Revenue Target | Risk Level
1 | Jul 2026 | Company registration, CA retainer, AWS setup, hire Eng #1, 5 pilot dealer outreach | MCA registration, bank account, GitHub org, first engineer start, 5 WhatsApp conversations with dealers | Company legally operational. First engineer writing code. | ₹0 | 🔴 HIGH
2 | Aug 2026 | Build ServicePulse MVP v0.1. Hire Eng #2. Sign 3 pilot agreements. | Working job card creation flow (no UI yet). 3 signed pilot letters. Domain expert hired. | Demo: voice complaint → job card → WhatsApp update working end-to-end. | ₹0 | 🔴 HIGH
3 | Sep 2026 | Complete ServicePulse MVP. Install at 2 pilot dealers. Begin Tamil Voice Agent. | Live at 2 dealers with real vehicles. 50+ job cards created. Voice agent prototype. | First real job card created in AutoEra AI. Not perfect — but working. | ₹0 | 🟠 HIGH
4 | Oct 2026 | Scale to 5 pilot dealers. Tamil Voice Agent live. Begin monetisation conversation. | 5 dealers using product daily. AI making outbound calls. First pricing presentation. | Product validated: dealers use it without being asked. Begin ₹2,499/month conversation. | ₹12,500 | 🟠 MED
5 | Nov 2026 | First 5 paying dealers. ₹1.2L MRR milestone. CS Manager hired. | 5 dealers paying ₹2,499/month. CS Manager start. First NPS survey sent. | FIRST REVENUE COLLECTED. Survival signal confirmed. | ₹1,25,000 | 🟡 MED
6 | Dec 2026 | 10 paying dealers. ₹2.5L MRR. InsureGuard beta. Angel investor conversations. | 10 paying dealers. InsureGuard demo at 3 dealers. Angel deck ready. | PMF signal beginning. Two months of positive retention. | ₹2,50,000 | 🟡 MED
7 | Jan 2027 | 20 paying dealers. Angel round close target. InsureGuard live. | 20 dealers paying. ₹50L angel investment closed. InsureGuard generating commission. | ₹50L in bank. 20 dealers. Gross margin confirmed >65%. | ₹5,00,000 | 🟡 MED
8 | Feb 2027 | 30 paying dealers. NPS survey #2. Series A deck started. | 30 dealers. NPS >40 confirmed. Series A deck v1 complete. 3 organic referrals. | PMF SIGNAL CONFIRMED: NPS >40, churn <3%, 3 referrals. | ₹7,50,000 | 🟢 MED
9 | Mar 2027 | 40 dealers. FinanceFlow beta. Begin Series A conversations. | 40 dealers paying. FinanceFlow processing first loan applications. 3 VC meetings booked. | ₹10L MRR. Series A process started. Unit economics proven. | ₹10,00,000 | 🟢 LOW
10 | Apr 2027 | 50 dealers. ₹12.5L MRR. Series A term sheet target. | 50 Chennai dealers confirmed. Series A term sheet from 1–2 VCs. | 50-dealer milestone. Anna Nagar + T. Nagar + Porur cluster owned. | ₹12,50,000 | 🟢 LOW
11 | May 2027 | Series A due diligence. InsureGuard premium analytics. Expand to Coimbatore. | Series A due diligence active. 5 CBE dealer outreach. FinanceFlow full launch. | Series A process 80% complete. National expansion planning starts. | ₹14,00,000 | 🟢 LOW
12 | Jun 2027 | Series A CLOSED. 65 dealers. ₹15L MRR. CTO hired. | Series A funds received. CTO joins. National expansion plan v1. | SERIES A CLOSED. 12-month runway extended to 3+ years. | ₹15,00,000 | 🟢 LOW
13 | Jul 2027 | National team hiring: VP Sales + 3 regional BDs. 80 dealers. | VP Sales joined. 3 regional BDs (CBE, BLR, HYD). 80 dealers. | National expansion engine activated. First out-of-Chennai dealers. | ₹20,00,000 | 🟡 MED
14 | Aug 2027 | 100 dealers. FleetIQ beta with 3 fleet operators. ₹25L MRR. | 100 active paying dealers. FleetIQ beta live. Fleet data pipeline operational. | Triple-digit dealer milestone. FleetIQ revenue potential confirmed. | ₹25,00,000 | 🟡 MED
15 | Sep 2027 | 150 dealers. OEM outreach: Hyundai Cradle + Maruti meeting. | 150 paying dealers. First OEM meeting conducted. FleetIQ 10 fleet vehicles. | ₹37L MRR. OEM conversations live. Fleet product validated. | ₹37,50,000 | 🟡 MED
16 | Oct 2027 | 200 dealers. EVIntel beta. Analytics Hub v2. | 200 paying dealers. EVIntel installed at 5 EV dealerships. Analytics Hub dashboard. | ₹50L MRR. EV module differentiation confirmed. | ₹50,00,000 | 🟢 LOW
17 | Nov 2027 | 250 dealers. First OEM pilot agreement. | 250 dealers. Hyundai Cradle pilot agreement signed (₹50L deal). EVIntel live. | FIRST OEM DEAL. Market validation for enterprise strategy. | ₹60,00,000 | 🟢 LOW
18 | Dec 2027 | 300 dealers. ₹75L MRR. Series A fully deployed. | 300 paying dealers across South India. Full team of 35. Annual review. | Year 1 post-Series A: 300 dealers, ₹9Cr ARR. On track for ₹40Cr Year 3. | ₹75,00,000 | 🟢 LOW
19 | Jan 2028 | 400 dealers. North India BD team. Series B planning starts. | 400 dealers. Delhi NCR BD team established. Series B financial model. | ₹1Cr MRR crossed. Series B target: ₹75–150Cr. | ₹1,00,00,000 | 🟢 LOW
20 | Feb 2028 | 500 dealers. Second OEM pilot (Maruti or Tata). | 500 dealers. Second OEM pilot agreement. CFO hired. | ₹1.25Cr MRR. Two OEM pilots running simultaneously. | ₹1,25,00,000 | 🟢 LOW
21 | Mar 2028 | 600 dealers. FleetIQ v2 with predictive maintenance. | 600 dealers. LSTM predictive model live (88% accuracy target). CFO completing. | ₹1.5Cr MRR. Predictive maintenance differentiator proven. | ₹1,50,00,000 | 🟢 LOW
22 | Apr 2028 | 700 dealers. International research: UAE market analysis. | 700 dealers. UAE market research report. Arabic language prototype. | ₹1.75Cr MRR. International expansion thesis confirmed. | ₹1,75,00,000 | 🟢 LOW
23 | May 2028 | 800 dealers. Series B roadshow. | 800 dealers. Series B investor roadshow: 20 meetings. Mumbai + Delhi + Singapore. | ₹2Cr MRR. Series B conversations from position of strength. | ₹2,00,00,000 | 🟢 LOW
24 | Jun 2028 | Series B CLOSED. 900 dealers. ₹2.25Cr MRR. | Series B ₹75Cr closed. 900 dealers. Year 2 review. | SERIES B CLOSED. International expansion capital secured. | ₹2,25,00,000 | 🟢 LOW
25 | Jul 2028 | UAE market entry | UAE office + 5 UAE dealers | First international revenue | ₹2,50,00,000 | 🟡 MED
26 | Month 26 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
27 | Month 27 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
28 | Month 28 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
29 | Month 29 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
30 | Dec 2028 | 250 UAE dealers | UAE InsureGuard live | ₹35L MRR international | ₹3,00,00,000 | 🟡 MED
31 | Month 31 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
32 | Month 32 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
33 | Month 33 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
34 | Month 34 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
35 | Month 35 | Dealer growth + platform expansion — Year 3 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
36 | Jun 2029 | 1,500 India dealers + 300 UAE | FleetIQ v3 + autonomous alerts | ₹4Cr MRR total | ₹4,00,00,000 | 🟢 LOW
37 | Month 37 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
38 | Month 38 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
39 | Month 39 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
40 | Month 40 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
41 | Month 41 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
42 | Dec 2029 | 2,500 dealers globally | Series B fully deployed | ₹5.5Cr MRR | ₹5,50,00,000 | 🟢 LOW
43 | Month 43 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
44 | Month 44 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
45 | Month 45 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
46 | Month 46 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
47 | Month 47 | Dealer growth + platform expansion — Year 4 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
48 | Jun 2030 | 3,500 dealers, SEA entry | Singapore + Indonesia pilot | ₹7.5Cr MRR | ₹7,50,00,000 | 🟢 LOW
49 | Month 49 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
50 | Month 50 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
51 | Month 51 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
52 | Month 52 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
53 | Month 53 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
54 | Dec 2030 | 5,000 dealers globally | Series C evaluation | ₹10Cr MRR target | ₹10,00,00,000 | 🟢 LOW
55 | Month 55 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
56 | Month 56 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
57 | Month 57 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
58 | Month 58 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
59 | Month 59 | Dealer growth + platform expansion — Year 5 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
60 | Jun 2031 | 6,500 dealers, API platform | Developer marketplace live | ₹14Cr MRR | ₹14,00,00,000 | 🟢 LOW
61 | Month 61 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
62 | Month 62 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
63 | Month 63 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
64 | Month 64 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
65 | Month 65 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
66 | Dec 2031 | 8,000 dealers, profitable | Operating cash flow positive | ₹18Cr MRR | ₹18,00,00,000 | 🟢 LOW
67 | Month 67 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
68 | Month 68 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
69 | Month 69 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
70 | Month 70 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
71 | Month 71 | Dealer growth + platform expansion — Year 6 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
72 | Jun 2032 | 10,000 dealers globally | Pre-IPO audit starts | ₹22Cr MRR | ₹22,00,00,000 | 🟢 LOW
73 | Month 73 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
74 | Month 74 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
75 | Month 75 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
76 | Month 76 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
77 | Month 77 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
78 | Dec 2032 | 12,000 dealers | Independent board majority | ₹28Cr MRR | ₹28,00,00,000 | 🟢 LOW
79 | Month 79 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
80 | Month 80 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
81 | Month 81 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
82 | Month 82 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
83 | Month 83 | Dealer growth + platform expansion — Year 7 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
84 | Jun 2033 | 15,000 dealers | IPO roadshow preparation | ₹35Cr MRR | ₹35,00,00,000 | 🟢 LOW
85 | Month 85 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
86 | Month 86 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
87 | Month 87 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
88 | Month 88 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
89 | Month 89 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
90 | Dec 2033 | 18,000 dealers | IPO filed (SEBI/SEC) | ₹42Cr MRR | ₹42,00,00,000 | 🟢 LOW
91 | Month 91 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
92 | Month 92 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
93 | Month 93 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
94 | Month 94 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
95 | Month 95 | Dealer growth + platform expansion — Year 8 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
96 | Jun 2034 | IPO COMPLETE | Listed NSE or NASDAQ | Market cap ₹8,000Cr+ | ₹50Cr MRR | 🟢 LOW
97 | Month 97 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
98 | Month 98 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
99 | Month 99 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
100 | Month 100 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
101 | Month 101 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
102 | Dec 2034 | 22,000 dealers post-IPO | Post-IPO expansion capital | ₹58Cr MRR | ₹58,00,00,000 | 🟢 LOW
103 | Month 103 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
104 | Month 104 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
105 | Month 105 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
106 | Month 106 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
107 | Month 107 | Dealer growth + platform expansion — Year 9 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
108 | Jun 2035 | 26,000 dealers | Africa + LATAM entry | ₹70Cr MRR | ₹70,00,00,000 | 🟢 LOW
109 | Month 109 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
110 | Month 110 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
111 | Month 111 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
112 | Month 112 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
113 | Month 113 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
114 | Dec 2035 | 30,000 dealers globally | AutoEra = global standard | ₹85Cr MRR | ₹85,00,00,000 | 🟢 LOW
115 | Month 115 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
116 | Month 116 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
117 | Month 117 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
118 | Month 118 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
119 | Month 119 | Dealer growth + platform expansion — Year 10 | Monthly targets met per annual plan | Compound growth on existing trajectory | Per plan | 🟢 LOW
120 | Jun 2036 | 35,000 dealers | Unicorn confirmed at IPO | ₹100Cr+ MRR | ₹1,00,00,00,000 | 🟢 LOW

## 📊 KPI Dashboard
AUTOERA AI — INVESTOR-GRADE KPI DASHBOARD ¦ Update Weekly
NORTH STAR METRICS
KPI | Formula | Frequency | Target | Owner | Status | Current | Goal
Monthly Recurring Revenue (MRR) | MRR = Σ(active dealer monthly fee) | Weekly | ₹8L by M12 | CEO | 🔴 Not Started | ₹0 | ₹8L
Annual Recurring Revenue (ARR) | ARR = MRR × 12 | Monthly | ₹96L by M12 | CEO | 🔴 Not Started | ₹0 | ₹96L
Active Paying Dealers | Count of dealers who paid in last 30 days | Weekly | 50 by M12 | Sales Head | 🔴 Not Started | 0 | 50
MRR Growth Rate (MoM) | (Current MRR − Last MRR) / Last MRR | Weekly | >15% MoM | CEO | ⚪ N/A | N/A | 15%
Net Revenue Retention (NRR) | (Start MRR + Expansion − Churn) / Start MRR | Monthly | >110% | CS Manager | ⚪ N/A | N/A | 110%
SURVIVAL METRICS
KPI | Formula | Frequency | Target | Owner | Status | Current | Goal
Monthly Net Burn Rate | Total cash out − Revenue | Weekly | <₹7L/month | CEO + CA | 🟡 Active | ₹7.2L | <₹7L
Cash in Bank | Actual bank balance | Daily | Always >12mo runway | CEO | 🟡 Active | ₹2Cr | ₹2Cr
Runway (months) | Cash in bank / Monthly net burn | Weekly | >12 months always | CEO | 🟡 Active | 22 months | 22
Gross Margin % | (Revenue − COGS) / Revenue | Monthly | >65% | CFO / CA | ⚪ N/A | N/A | 65%
Monthly Churn Rate | Churned MRR / Beginning MRR | Monthly | <3%/month | CS Manager | ⚪ N/A | N/A | 3%
PRODUCT METRICS
KPI | Formula | Frequency | Target | Owner | Status | Current | Goal
Daily Active Users (DAU) | Dealers logging in or using AI agent daily | Daily | >70% of paying dealers | CPO | ⚪ N/A | N/A | 70%
Job Cards Created Per Day | Total job cards across all dealers | Daily | >50/day by M6 | CPO | ⚪ N/A | 0 | 50/day
AI Agent Success Rate | % of AI actions completed without human intervention | Weekly | >85% | AI Engineer | ⚪ N/A | N/A | 85%
WhatsApp Delivery Rate | % of auto-messages successfully delivered | Daily | >98% | Engineering | ⚪ N/A | N/A | 98%
NPS Score | Net Promoter Score — quarterly survey | Quarterly | >50 | CS Manager | ⚪ N/A | N/A | 50
SALES METRICS
KPI | Formula | Frequency | Target | Owner | Status | Current | Goal
Customer Acquisition Cost (CAC) | Total sales+mktg spend / New dealers | Monthly | <₹15,000 | Sales Head | ⚪ N/A | N/A | ₹15K
Sales Cycle Length | Days from first contact to signed contract | Monthly | <30 days | Sales Head | ⚪ N/A | N/A | 30 days
Lead-to-Demo Conversion | Demos / Qualified leads | Weekly | >40% | Sales Head | ⚪ N/A | N/A | 40%
Demo-to-Pilot Conversion | Pilots / Demos conducted | Weekly | >60% | Sales Head | ⚪ N/A | N/A | 60%
Pilot-to-Paid Conversion | Paid / Pilots completed | Monthly | >80% | CS Manager | ⚪ N/A | N/A | 80%
LTV:CAC Ratio | Customer LTV / CAC | Quarterly | >5x | CFO | ⚪ N/A | N/A | 5x
ENGINEERING METRICS
KPI | Formula | Frequency | Target | Owner | Status | Current | Goal
API Uptime | % of time API is available and responsive | Daily | >99.9% | CTO / DevOps | ⚪ N/A | N/A | 99.9%
Sprint Velocity | Story points completed per 2-week sprint | Bi-weekly | Stable or improving | CTO | ⚪ N/A | N/A | Stable
Bug Resolution Time (P1) | Hours to fix critical bugs | Daily | <4 hours for P1 | Engineering | ⚪ N/A | N/A | <4hrs
Feature Deployment Frequency | Production deployments per week | Weekly | ≥2/week | CTO | ⚪ N/A | N/A | 2/week
AI Model Accuracy | % predictions rated correct by users | Weekly | >85% by M9 | AI Engineer | ⚪ N/A | N/A | 85%
BOARD-LEVEL METRICS
KPI | Formula | Frequency | Target | Owner | Status | Current | Goal
Investor Updates Sent | Monthly updates sent on time (by 5th) | Monthly | 100% on time | CEO | ⚪ N/A | N/A | 100%
Board Meeting Frequency | Meetings held per quarter | Quarterly | 4 per year minimum | CEO | ⚪ N/A | N/A | 4/year
Statutory Compliance | GST + TDS + ROC filed on time | Monthly | 0 late filings | CA | 🟡 Active | On track | 0 late
Capital Efficiency (ARR/₹ invested) | ARR / Total investment consumed | Quarterly | ₹2 ARR per ₹1 invested by Y2 | CFO | ⚪ N/A | N/A | 2:1

## 🎯 OKR System
AUTOERA AI — OKR SYSTEM ¦ Q3 2026 (Jul–Sep) ¦ Foundation Quarter
FOUNDER / CEO OKRs — Q3 2026 (Jul–Sep)
Objective | Key Results | Owner | Score | Status | Deadline | Notes
O1: Achieve first revenue signal | KR1: 5 dealers paying ₹2,499+/month by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: ₹1.25L MRR confirmed by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: Gross margin >65% proven on first 5 dealers | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: CAC < ₹15,000 for first cohort | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
O2: Build the founding team | KR1: Full-stack Engineer #1 hired by Jul 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Automotive Domain Expert hired by Jul 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: Full-stack Engineer #2 hired by Aug 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: CA retainer engaged by Jul 7 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
O3: Establish legal + financial foundation | KR1: Pvt Ltd registered by Jul 10 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Company bank account opened by Jul 14 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: GST registration complete by Jul 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: First board meeting conducted by Aug 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
ENGINEERING OKRs — Q3 2026 (Jul–Sep)
Objective | Key Results | Owner | Score | Status | Deadline | Notes
O1: Ship ServicePulse MVP | KR1: Job card creation working end-to-end by Aug 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: WhatsApp 6-stage update automation live by Aug 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: Number plate OCR accuracy >90% by Sep 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: First dealer installed and using daily by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
O2: Build reliable infrastructure | KR1: AWS Mumbai setup with RDS + S3 by Jul 20 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: CI/CD pipeline live (GitHub Actions) by Jul 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: 99.9% uptime achieved in Aug and Sep | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: Zero P1 incidents lasting >2 hours in Q3 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
O3: Tamil Voice Agent prototype | KR1: Sarvam AI / Whisper ASR integrated by Sep 1 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Agent makes first 10 test calls by Sep 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: Tamil speech recognition accuracy >80% in test | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: Call outcome logging in CRM working by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
SALES OKRs — Q3 2026 (Jul–Sep)
Objective | Key Results | Owner | Score | Status | Deadline | Notes
O1: Validate willingness to pay | KR1: 50 dealer discovery calls conducted by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: 10 product demos delivered by Sep 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: 5 pilot agreements signed (unpaid) by Aug 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: 5 paid conversions at ₹2,499+ by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
O2: Build the sales playbook | KR1: 60-second verbal pitch memorised and tested on 20 dealers | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: First dealer case study (with ₹ ROI numbers) written by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: FADA TN chapter presentation delivered by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: Outreach CRM set up with 100+ dealer contacts by Aug 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
PRODUCT OKRs — Q3 2026 (Jul–Sep)
Objective | Key Results | Owner | Score | Status | Deadline | Notes
O1: Prove product usability | KR1: Service Advisor creates job card in <90 seconds by Sep 1 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Customer receives WhatsApp within 30 seconds of job card creation | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: First NPS survey — minimum 3 responses — by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: Tamil Voice Agent makes 50 outbound calls in Q3 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
O2: Document product requirements | KR1: Full PRD for ServicePulse v1 written and approved by Aug 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Tamil Voice Agent feature spec complete by Aug 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: InsureGuard module wireframes complete by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: Mobile app wireframes (Service Advisor) complete by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
FINANCE OKRs — Q3 2026 (Jul–Sep)
Objective | Key Results | Owner | Score | Status | Deadline | Notes
O1: Financial discipline from Day 1 | KR1: Monthly P&L produced for Jul, Aug, Sep — by 5th of each following month | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Burn rate tracked weekly — within ₹10K accuracy | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: Capital Allocation — 100% of spending within budget categories | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: 18+ months runway maintained throughout Q3 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
O2: Non-dilutive capital secured | KR1: AWS Activate application submitted by Jul 10 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Microsoft for Startups approved by Jul 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: Google for Startups credits active by Aug 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: StartupTN Elevate application submitted by Aug 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
AI TEAM OKRs — Q3 2026 (Jul–Sep)
Objective | Key Results | Owner | Score | Status | Deadline | Notes
O1: Core AI infrastructure built | KR1: WhatsApp Business API (Gupshup) integrated and tested by Aug 31 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR2: Gemini Flash routing live for all Starter tier requests by Sep 15 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR3: RAG pipeline for service manual Q&A working by Sep 30 | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]
| KR4: AI suggestion accuracy baseline measured (first 100 suggestions) | SJ / Team | 0.0 / 1.0 | 🔴 Not Started | Sep 30, 2026 | [Update weekly]

## ✅ Task Manager
AUTOERA AI — TASK MANAGEMENT SYSTEM ¦ Sprint 1 & 2 ¦ Jul–Aug 2026
ID | Task Name | Epic | Sprint | Priority | Status | Owner | Est Hrs | Act Hrs | Dependencies | Biz Value | Risk | Automation?
T001 | Register AutoEra AI Solutions Pvt Ltd | Legal & Compliance | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 4 | 0 | None | Unlocks all company activities | LOW | No
T002 | Open company current account (HDFC/Kotak) | Legal & Compliance | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 2 | 0 | T001 | Receive investment + pay salaries | LOW | No
T003 | Engage CA on monthly retainer | Legal & Compliance | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 3 | 0 | T001 | GST, TDS, compliance | LOW | No
T004 | Register on DPIIT Startup India portal | Legal & Compliance | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 2 | 0 | T001 | Tax holiday + grant eligibility | LOW | No
T005 | Apply AWS Activate ($100K credits) | Infrastructure | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 1 | 0 | T001 | ₹80L cloud cost saved | LOW | Yes
T006 | Apply Microsoft for Startups ($150K) | Infrastructure | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 1 | 0 | T001 | ₹1.2Cr Azure credits free | LOW | Yes
T007 | Apply Google for Startups (GCP credits) | Infrastructure | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 1 | 0 | T001 | Free AI API access | LOW | Yes
T008 | Set up AWS Mumbai (RDS + S3 + VPC) | Infrastructure | Sprint 1 | P0 — CRITICAL | 🔴 TODO | Eng #1 | 8 | 0 | T005 | Platform foundation | MED | Partial
T009 | GitHub organisation + CI/CD pipeline | Infrastructure | Sprint 1 | P0 — CRITICAL | 🔴 TODO | Eng #1 | 6 | 0 | T008 | Code quality + deployment speed | LOW | Yes
T010 | Interview + hire Engineer #1 (FastAPI) | Hiring | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 16 | 0 | T001, T002 | Core platform build | HIGH | No
T011 | Interview + hire Automotive Domain Expert | Hiring | Sprint 1 | P0 — CRITICAL | 🔴 TODO | SJ | 12 | 0 | T001 | Dealer network + product validation | HIGH | No
T012 | Set up accounting in Zoho Books | Finance | Sprint 1 | P1 — HIGH | 🔴 TODO | CA | 4 | 0 | T002, T003 | Clean books from Day 1 | LOW | Partial
T013 | WhatsApp Business API (Gupshup) setup | Product — ServicePulse | Sprint 1 | P1 — HIGH | 🔴 TODO | Eng #1 | 8 | 0 | T008 | Core communication channel | MED | Yes
T014 | Interview + hire Engineer #2 (Mobile) | Hiring | Sprint 2 | P1 — HIGH | 🔴 TODO | SJ | 12 | 0 | T010 | Mobile app development | HIGH | No
T015 | Number plate OCR module (OpenCV + AWS Rekognition) | Product — ServicePulse | Sprint 2 | P0 — CRITICAL | 🔴 TODO | Eng #1 | 16 | 0 | T008 | 90-sec job card start point | MED | Yes
T016 | Voice complaint capture (Sarvam AI / Whisper) | Product — ServicePulse | Sprint 2 | P0 — CRITICAL | 🔴 TODO | Eng #1 | 12 | 0 | T008 | Voice-to-text for complaints | MED | Yes
T017 | Job card database schema (PostgreSQL) | Product — ServicePulse | Sprint 2 | P0 — CRITICAL | 🔴 TODO | Eng #1 | 8 | 0 | T008 | Data model foundation | LOW | No
T018 | 6-stage WhatsApp automation workflow | Product — ServicePulse | Sprint 2 | P0 — CRITICAL | 🔴 TODO | Eng #1 | 12 | 0 | T013, T017 | Zero-inbound calls from customers | MED | Yes
T019 | Sign 3 pilot dealer agreements (unpaid) | Sales | Sprint 2 | P0 — CRITICAL | 🔴 TODO | SJ | 8 | 0 | T011 | First user feedback | MED | No
T020 | Apply StartupTN Elevate programme | Funding | Sprint 2 | P1 — HIGH | 🔴 TODO | SJ | 3 | 0 | T001, T004 | ₹30L non-dilutive grant | LOW | Partial
T021 | Apply NASSCOM 10K Startup | Funding | Sprint 2 | P1 — HIGH | 🔴 TODO | SJ | 2 | 0 | T001 | Enterprise network + credibility | LOW | No
T022 | Apply MeitY TIDE 2.0 NIT Trichy | Funding | Sprint 2 | P1 — HIGH | 🔴 TODO | SJ | 3 | 0 | T001, T004 | ₹25L non-dilutive grant | LOW | No
T023 | Email IIT Madras Incubation Cell | Funding | Sprint 2 | P1 — HIGH | 🔴 TODO | SJ | 2 | 0 | T001 | Chennai incubator + IITM network | LOW | No
T024 | Basic admin dashboard (React) | Product — ServicePulse | Sprint 2 | P1 — HIGH | 🔴 TODO | Eng #2 | 20 | 0 | T017 | Dealer sees job cards on screen | MED | Partial
T025 | First dealer demo — working product | Sales | Sprint 2 | P0 — CRITICAL | 🔴 TODO | SJ + Domain Expert | 4 | 0 | T015,T016,T018 | Proof dealers want this | HIGH | No

## 🛠️ Product Roadmap
AUTOERA AI — PRODUCT ROADMAP ¦ RICE + MoSCoW + ICE Prioritisation
Feature / Module | Status | Phase | RICE Score | MoSCoW | Reach | Impact | Confidence | Effort (wks) | ICE Score | Team
ServicePulse — 90-sec Job Card | P0 Live | MVP | 9,200 | Must Have | 9/10 | 10/10 | 9/10 | 3 wks | 864 | Eng #1 + Domain
6-Stage WhatsApp Auto-Updates | P0 Live | MVP | 8,800 | Must Have | 10/10 | 9/10 | 9/10 | 2 wks | 810 | Eng #1
Number Plate OCR Scanner | P0 Live | MVP | 7,200 | Must Have | 9/10 | 8/10 | 9/10 | 2 wks | 720 | Eng #1
Tamil Voice Follow-up Agent | P0 Live | MVP | 8,100 | Must Have | 9/10 | 9/10 | 8/10 | 3 wks | 729 | AI Eng
InsureGuard — Renewal Automation | P1 Q2 | Growth | 7,400 | Must Have | 8/10 | 9/10 | 8/10 | 3 wks | 672 | Eng #1
Multi-Insurer Quote Comparison | P1 Q2 | Growth | 6,800 | Must Have | 8/10 | 8/10 | 8/10 | 2 wks | 640 | Eng #1
AI Lead Scoring (1–10) | P1 Q2 | Growth | 7,000 | Must Have | 9/10 | 8/10 | 8/10 | 3 wks | 648 | AI Eng
SalesMind CRM — Full Pipeline | P1 Q2 | Growth | 6,500 | Should Have | 8/10 | 8/10 | 7/10 | 4 wks | 560 | Eng #2
FinanceFlow — DigiLocker | P1 Q2 | Growth | 6,200 | Should Have | 7/10 | 8/10 | 8/10 | 3 wks | 560 | Eng #2
Analytics Dashboard — DP Brief | P1 Q2 | Growth | 5,800 | Should Have | 8/10 | 7/10 | 8/10 | 3 wks | 504 | Eng #2
Service Advisor Mobile App | P1 Q2 | Growth | 6,000 | Should Have | 8/10 | 8/10 | 7/10 | 3 wks | 560 | Eng #2
Customer WhatsApp App | P1 Q2 | Growth | 5,500 | Should Have | 9/10 | 7/10 | 7/10 | 4 wks | 441 | Eng #2
FleetIQ — GPS + OBD-II | P2 Q3 | Scale | 5,200 | Should Have | 6/10 | 9/10 | 7/10 | 5 wks | 378 | Eng #3
Predictive Maintenance (LSTM) | P2 Q3 | Scale | 4,800 | Should Have | 6/10 | 9/10 | 6/10 | 8 wks | 270 | AI Eng
EVIntel — Battery Health | P2 Q3 | Scale | 4,500 | Could Have | 5/10 | 9/10 | 7/10 | 6 wks | 315 | AI Eng
Fuel Theft Detection | P2 Q3 | Scale | 4,200 | Could Have | 5/10 | 8/10 | 7/10 | 4 wks | 280 | Eng #3
OEM Dashboard | Backlog | Year 2 | 3,800 | Should Have | 4/10 | 9/10 | 6/10 | 8 wks | 216 | Eng #4+
AI Damage Assessment (Vision) | Backlog | Year 2 | 3,500 | Could Have | 5/10 | 8/10 | 6/10 | 8 wks | 210 | AI Eng
Developer API Platform | Backlog | Year 3 | 3,000 | Could Have | 4/10 | 9/10 | 6/10 | 10 wks | 180 | Arch
Global Localisation (Arabic/Bahasa) | Backlog | Year 4 | 2,500 | Won't Have (now) | 3/10 | 9/10 | 5/10 | 12 wks | 112 | Eng Team

## 💼 Sales CRM
AUTOERA AI — SALES CRM ¦ Dealer Pipeline Tracker ¦ Update Daily
PIPELINE STAGE DEFINITIONS ¦ Conversion Targets
🔍 PROSPECT | Identified as potential customer. Not yet contacted. | [5 empty] | Contact within 48hrs |  |  | Target: —
📞 QUALIFIED | Pain confirmed in discovery call. Budget >₹2,500/month. Decision maker identified. | [5 empty] | Book demo within 5 days |  |  | Target: —
🖥️ DEMO | Product demo delivered. Dealer saw live 90-sec job card. | [5 empty] | Follow up within 24hrs |  |  | Target: 60% of Qualified
📋 PROPOSAL | Pricing sent. Contract draft shared. | [5 empty] | Follow up in 48hrs |  |  | Target: 75% of Demo
🤝 NEGOTIATION | Dealer wants changes to price or terms. | [5 empty] | Resolve within 5 days |  |  | Target: 80% of Proposal
🧪 PILOT | 90-day free pilot started. Real dealers using daily. | [5 empty] | Check in weekly |  |  | Target: 90% of Negotiation
✅ CUSTOMER | First payment received. Active paying subscriber. | [5 empty] | Monthly NPS + CS check |  |  | Target: 85% of Pilot
📈 EXPANSION | Customer paying for additional modules. | [5 empty] | Quarterly upsell review |  |  | Target: 30% of Customers/year
🔄 RENEWAL | Annual contract renewal. | [5 empty] | Contact 90 days before |  |  | Target: 85% renewal target
❌ LOST | Did not convert. Reason documented. | [5 empty] | Re-engage at D+60 |  |  | Target: —
DEALER PIPELINE — LIVE CRM TRACKER
# | Dealer Name | Location | Contact Name | Phone/Email | Stage | MRR Potential | Demo Date | Last Contact | Next Action | Pilot Interest | Lost Reason | Notes
1 | [Dealer Name 1] | Anna Nagar, Chennai | [Contact Name] | [Phone/Email] | 🔍 PROSPECT | ₹5,000/mo | — | — | Call this week | High | — | Hyundai dealer, 3 service advisors
2 | [Dealer Name 2] | T. Nagar, Chennai | [Contact Name] | [Phone/Email] | 🔍 PROSPECT | ₹7,500/mo | — | — | WhatsApp intro | High | — | Multi-brand, 5 advisors
3 | [Dealer Name 3] | Porur, Chennai | [Contact Name] | [Phone/Email] | 📞 QUALIFIED | ₹5,000/mo | Book demo | Yesterday | Demo this week | Very High | — | Pain confirmed: missing 30% leads
4 | [Dealer Name 4] | Valasaravakkam | [Contact Name] | [Phone/Email] | 🖥️ DEMO | ₹7,500/mo | Done | 2 days ago | Send proposal | Very High | — | Loved 90-sec job card demo
5 | [Dealer Name 5] | OMR, Chennai | [Contact Name] | [Phone/Email] | 🧪 PILOT | ₹10,000/mo | Done | Today | Weekly check-in | Committed | — | Pilot started M1W3. 15 job cards done.
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## 💰 Financial Dashboard
AUTOERA AI — MONTHLY FINANCIAL DASHBOARD ¦ Live Operating Tracker
METRIC | M1 Jul | M2 Aug | M3 Sep | M4 Oct | M5 Nov | M6 Dec | M7 Jan | M8 Feb | M9 Mar | M10 Apr | M11 May | M12 Jun
── REVENUE ──
MRR (₹ Lakhs) | 0 | 0 | 0 | 0.12 | 0.25 | 0.5 | 1 | 2 | 3.5 | 5 | 7 | 8
ARR Run-Rate (₹ L) | 0 | 0 | 0 | 1.4 | 3 | 6 | 12 | 24 | 42 | 60 | 84 | 96
Active Paying Dealers | 0 | 0 | 0 | 5 | 10 | 20 | 40 | 80 | 140 | 200 | 280 | 320
Avg MRR/Dealer (₹) | 0 | 0 | 0 | 24000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
── COSTS ──
Engineering Salaries (₹L) | 1.65 | 1.65 | 2.45 | 2.45 | 2.45 | 3.25 | 3.25 | 3.25 | 4.05 | 4.05 | 4.05 | 5.5
AI APIs + Cloud Infra (₹L) | 0.83 | 1 | 1 | 1.2 | 1.2 | 1.4 | 1.6 | 1.8 | 2 | 2.2 | 2.4 | 2.6
Sales + Marketing (₹L) | 0.25 | 0.25 | 0.5 | 0.75 | 0.75 | 1 | 1.5 | 1.5 | 2 | 2 | 2.5 | 2.5
Operations + Legal (₹L) | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.55 | 0.6 | 0.6 | 0.65 | 0.65 | 0.7 | 0.7
Customer Success (₹L) | 0 | 0 | 0.6 | 0.6 | 0.6 | 0.65 | 0.65 | 0.65 | 0.7 | 0.7 | 0.75 | 0.75
TOTAL OPEX (₹ Lakhs) | 3.28 | 3.45 | 5.1 | 5.55 | 5.55 | 6.85 | 7.6 | 7.8 | 9.4 | 9.6 | 10.4 | 12.05
── CASH ──
Gross Burn (₹L/month) | 5.5 | 6 | 6.5 | 6.8 | 6.8 | 7.5 | 8 | 8.2 | 9.5 | 9.6 | 10.5 | 12.1
Net Burn (₹L/month) | 5.5 | 6 | 6.5 | 6.68 | 6.55 | 7 | 7 | 6.2 | 6 | 4.6 | 3.5 | 4.1
Cash in Bank (₹L) | 200 | 194 | 187.5 | 180.8 | 174.2 | 167.2 | 160.2 | 154 | 148 | 143.4 | 139.9 | 135.8
Runway (months) | 36 | 32 | 29 | 27 | 27 | 22 | 20 | 19 | 16 | 15 | 13 | 11
Gross Margin % | 0% | 0% | 0% | 62% | 63% | 64% | 64% | 65% | 66% | 67% | 68% | 68%
── ACTUALS (Blue = Input) ──
ACTUAL MRR (₹L)
ACTUAL Burn (₹L)
ACTUAL Cash (₹L)
VARIANCE: MRR (₹L)

## ⚠️ Risk Register
AUTOERA AI — ENTERPRISE RISK REGISTER ¦ Live Monitoring ¦ Update Monthly
# | Risk Description | Category | Probability | Impact | Risk Score | Severity | Mitigation Plan | Owner + Review Date
1 | Dealer adoption slower than modelled — technicians resist software | Product / Market | 45% | 85% | 38 | 🔴 CRITICAL | Build 30-sec job card as primary KPI. Tamil CS Manager visits every dealer weekly M1. Printed Tamil quick-reference cards at every workstation. If <5 daily users by M3: immediate UX sprint. | SJ + CS Manager ¦ Monthly
2 | AI API costs spike — GPT-4o usage exceeds ₹800/dealer/month | Financial | 35% | 70% | 25 | 🟠 HIGH | Hard cap: ₹800/dealer/month AI API budget enforced at infrastructure level. Starter tier = Gemini Flash only. Weekly cost dashboard. Automatic fallback if budget exceeded. | CTO ¦ Weekly
3 | Key engineer quits in first 6 months | People | 30% | 90% | 27 | 🟠 HIGH | ESOP with 1-year cliff. No single point of knowledge failure (pair programming mandatory). Document every module. 2-week notice minimum. Second engineer hired M2 as redundancy. | SJ ¦ Monthly
4 | MVP takes >120 days to build | Product | 50% | 70% | 35 | 🔴 CRITICAL | MVP = ServicePulse ONLY (job card + WhatsApp). Cut Tamil Voice Agent to Month 3 if needed. First dealer live by Day 60 even if ugly. Ship minimum viable, iterate weekly. | CTO ¦ Weekly
5 | Cash runs out before Series A | Financial | 25% | 95% | 24 | 🟠 HIGH | Milestone-gated spending. Emergency reserve ₹18L locked. Weekly cash position review. Start Series A conversations at M8 (when 30 dealers confirmed). Never let runway fall below 9 months. | SJ + CA ¦ Weekly
6 | WhatsApp Business API disruption (Meta policy change) | Technology | 20% | 65% | 13 | 🟡 MEDIUM | Multi-channel fallback: SMS (Exotel), email, push notification. WhatsApp is primary, not only. API-first architecture allows channel swap in 2-week sprint. | CTO ¦ Quarterly
7 | DPDP Act compliance failure | Legal | 15% | 90% | 14 | 🟡 MEDIUM | Legal retainer from Day 1. Consent framework live before first dealer. Monthly compliance review with CA. DPDP audit at M6 and M12. Zero customer PII in logs. | CA + SJ ¦ Monthly
8 | OEM builds their own dealer AI (Maruti, Hyundai internal) | Competition | 35% | 55% | 19 | 🟡 MEDIUM | OEM AI serves new cars, not service centers. AutoEra AI is OEM-agnostic and works across all brands. Tamil + WhatsApp-first = OEM can't replicate without 3-year investment. | SJ ¦ Quarterly
9 | Founder burnout — SJ overloaded across all functions | Founder | 40% | 85% | 34 | 🔴 CRITICAL | 6-day work week maximum. Domain Expert hired to share operational load. Advisory board engaged by M3. Strict: no CEO tasks after 9pm. Weekly exercise non-negotiable. | SJ ¦ Weekly
10 | Competitor launches cheaper alternative | Competition | 25% | 50% | 13 | 🟡 MEDIUM | AutoEra AI's moat: Tamil language + WhatsApp-first + dealer relationships + data (after 6 months). Price is not the moat — workflow lock-in is. Retain > Acquire strategy. | SJ ¦ Quarterly
11 | Data breach — dealer customer PII exposed | Technology | 10% | 95% | 10 | 🟡 MEDIUM | AWS WAF + RLS + AES-256 from Day 1. Pen test at M6. Cyber insurance from M1. DPDP compliance. Pre-approved breach response runbook. Zero PII in client-side logs. | CTO ¦ Quarterly
12 | Key dealer churns after pilot — public complaint | Product | 35% | 65% | 23 | 🟠 HIGH | Mandatory exit interview. CS manager visits within 24 hours of churn. SJ personally calls churned dealer. Root cause analysis before next pilot onboarding. | CS Manager ¦ As needed
13 | Co-founder/key team dispute | People | 20% | 80% | 16 | 🟡 MEDIUM | Written founder agreement with vesting, IP assignment, dispute resolution clause. Board is arbiter. Monthly 1:1 SJ + each team member. Transparent OKR system prevents misalignment. | SJ ¦ Ongoing
14 | Government grant delays / rejections | Financial | 40% | 25% | 10 | 🟢 LOW | Apply to 5+ programmes simultaneously. No single grant > 15% of budget plan. Treat grants as upside, not baseline. If all rejected: runway still 18+ months from angel round. | SJ ¦ Per application
15 | AI model accuracy below 85% — dealer trust lost | AI / Product | 35% | 65% | 23 | 🟠 HIGH | Human-in-loop for all customer-facing outputs M1–M9. Confidence threshold: 85% before auto-send. Every AI suggestion shows confidence score. Model feedback loop from M1. | AI Engineer ¦ Weekly

## 📋 Weekly + Daily System
AUTOERA AI — CEO WEEKLY & DAILY OPERATING SYSTEM
WEEKLY CALENDAR — RECURRING CEO SCHEDULE
MONDAY | 6am–7am: Review last week actuals vs OKRs. 7am–9am: Deep work — strategy + financial model. 9am–10am: 1:1 with engineers (sprint review). 10am–12pm: Investor/partner outreach email batch. 12pm–1pm: Lunch + walk. 1pm–4pm: Product review — features in dev. 4pm–5pm: Team OKR standup (Monday rhythm). 5pm–6pm: Investor update draft (if week-of-update). | Weekly OKR dashboard updated. Top 3 priorities for week set. Engineer blockers resolved. | Revenue/burn numbers reviewed | CEO Planning Day
TUESDAY | 8am–10am: 3 dealer discovery calls (30 min each). 10am–12pm: Deep work — sales collateral improvement. 12pm–1pm: Lunch. 1pm–3pm: 2 dealer demos (if scheduled). 3pm–5pm: Follow-up emails/WhatsApp for all demos. 5pm–6pm: CRM update — all contacts touched today. | 3 discovery calls minimum. 1–2 demos. CRM 100% updated by 6pm. | New dealer pipeline added | Customer Discovery Day
WEDNESDAY | 8am–12pm: Deep work — product decisions, PRD writing, wireframe review. 12pm–1pm: Lunch. 1pm–3pm: Engineering standup + unblock sprint. 3pm–5pm: Customer feedback review — what did dealers say this week? 5pm–6pm: Voice agent test calls / AI model review. | Sprint blockers resolved. Product decisions documented. Customer feedback actioned. | 1 product decision per week | Product Day
THURSDAY | 8am–9am: Review sales pipeline — move every deal forward. 9am–12pm: Outbound: 10 dealer WhatsApp messages, 5 LinkedIn DMs, 3 emails. 12pm–1pm: Lunch. 1pm–3pm: 2 dealer demos or follow-up calls. 3pm–4pm: FADA/TiE networking call (bi-weekly). 4pm–6pm: Proposal/contract prep for deals in Negotiation. | 10 outbound messages sent. Pipeline updated. 1 deal moved forward. | MRR pipeline value reviewed | Sales Execution Day
FRIDAY | 8am–9am: Cash position check + burn rate update. 9am–11am: Expense approvals + CA discussion (weekly). 11am–12pm: Investor outreach for follow-up (weekly batch). 12pm–1pm: Lunch. 1pm–3pm: Team 1:1s (30 min each). 3pm–4pm: Week review — what shipped, what didn't. 4pm–5pm: Board/investor update if week 1 of month. | Burn rate updated. All expenses approved. Team 1:1s complete. | Cash position logged | Finance + Operations Day
SATURDAY | 8am–10am: Deep learning — 1 book chapter + 1 podcast. 10am–12pm: Industry article / AI research reading. 12pm–2pm: Personal time. 2pm–4pm: TiE Chennai / FADA / industry event (if scheduled). 4pm–6pm: LinkedIn content creation (1 post per week). 6pm–8pm: Mentor/advisor call (monthly). | 1 LinkedIn post published. 1 learning module completed. Network touchpoint made. | 1 new investor/dealer contact added | Learning + Networking Day
SUNDAY | 8am–9am: Weekly review journal — 3 wins, 3 lessons, 1 decision for next week. 9am–10am: Prioritise Monday tasks (not email — only priorities). Rest of day: family, exercise, no work screens after 11am. Minimum 8 hours sleep. Prepare for Monday. | Weekly journal complete. Monday top 3 priorities set. Zero work after 4pm. | Decision quality self-rating logged | Rest + Weekly Review Day
DAILY CEO ROUTINE — TIME-BLOCKED SCHEDULE
5:00am | Wake + No Phone | First 30 min: no screens. Journal, stretch, set intention for the day. | Clarity | Non-negotiable
5:30am | Exercise | 30–45 min: run, gym, or yoga. CEO health = company health. Skip this = decision quality drops 30%. | Energy | Non-negotiable
6:15am | Morning Review | Check: cash position (app), burn rate alert, any P1 system issue. 15 min max. | Situational awareness | Daily
6:30am | Deep Work Block 1 | 90 minutes of highest-priority work: strategy, PRD, investor deck, financial model. ZERO interruptions. Phone off. | 1 major output per morning | Every weekday
8:00am | Team Check-in | 15-minute standup: 3 questions — what did you do yesterday, what today, what's blocking you? | Blockers resolved by 9am | Daily
8:15am | Email + WhatsApp Batch | One focused batch: reply to investor, dealer, and team messages. Done in 30 min. Not checked again until 1pm. | 100% inbox actioned | 2× daily max
9:00am | Customer / Sales Block | Dealer calls, demos, discovery. This is the most revenue-generating 3 hours of the day. Guard it fiercely. | 3 customer interactions minimum | Tue/Thu priority
12:00pm | Lunch + Walk | 30-minute walk. No phone. Mental reset. Chennai's 1pm heat = indoor walk is fine. | Mental clarity | Daily
1:00pm | Email Batch 2 | Second and final email check of the day. 20 min max. | Zero unread critical | Daily
1:30pm | Product / Engineering | PRD review, demo review, AI model testing, sprint management. Unblock engineers. | 1 product decision documented | Mon/Wed
3:00pm | Deep Work Block 2 | 90 minutes: fundraising, investor update, financial model, board prep. No meetings. | 1 output delivered | Daily
4:30pm | Outbound Sales | 10 WhatsApp messages to warm dealer prospects. 3 LinkedIn DMs. 2 follow-up emails. | Pipeline moves forward | Daily
5:30pm | Team 1:1s | 30-min 1:1 with 1 team member per day (rotating). Coaching, feedback, blockers. | Team retention | Daily
6:30pm | Daily Review | 5 min journal: 3 wins today. 3 lessons. 1 decision made. Energy level 1–10. Sleep hours last night. | Self-awareness | Daily
7:00pm | Family / Personal | Hard stop. No screens after 8pm. This protects decision quality. Startups fail when founders burn out. | Sustainability | Non-negotiable
10:00pm | Sleep | 8 hours minimum. Sleep deprivation is the #1 hidden startup killer. CEOs who sleep 6 hours make worse decisions. | Cognitive performance | Non-negotiable

## 👥 Hiring Roadmap
AUTOERA AI — TEAM BUILDING ROADMAP ¦ Year 1–5 Hiring Plan
# | Role | Hire Month | Monthly Salary | Annual Cost | Type | Priority | ESOP % | ROI Justification
1 | CEO / Founder (SJ) | M1 | ₹50,000 | ₹6,00,000 | FTE | CRITICAL | 0% | Survival salary. Market rate only after Series A.
2 | Full-Stack Engineer #1 (FastAPI + React) | M1 | ₹55,000 | ₹6,60,000 | FTE | CRITICAL | 1.5% | Cannot build MVP without. Every week delayed = ₹55K lost.
3 | Full-Stack Engineer #2 (React Native + Mobile) | M2 | ₹50,000 | ₹6,00,000 | FTE | CRITICAL | 1.5% | Mobile app = Customer App + Advisor App = dealer daily use.
4 | Automotive Domain Expert (ex-Dealer GM/SM) | M1 | ₹65,000 | ₹7,80,000 | FTE | CRITICAL | 1.0% | Product decisions without this person will be wrong. Dealer network.
5 | UI/UX Designer (Figma specialist) | M1 | ₹20,000 | ₹1,20,000 | Freelance | HIGH | — | 6-month contract. Design system + 5 app screens.
6 | CA / GST / Accounting Retainer | M1 | ₹20,000 | ₹2,40,000 | Retainer | CRITICAL | — | ₹2Cr in bank without clean books = investor trust risk.
7 | Legal Counsel (startup specialist) | M1 | ₹25,000 | ₹3,00,000 | Retainer | CRITICAL | — | Contracts, ESOP, investor docs, DPDP compliance.
8 | AI/ML Engineer (NLP + LLM integration) | M3 | ₹80,000 | ₹9,60,000 | FTE | HIGH | 1.5% | Tamil Voice Agent + AI diagnosis = core differentiator.
9 | Customer Success Manager (Tamil-speaking) | M3 | ₹55,000 | ₹6,60,000 | FTE | HIGH | 0.75% | Dealer onboarding + retention = NRR driver. Best ROI hire.
10 | BD / Sales Executive (ex-OEM rep) | M4 | ₹45,000 | ₹5,40,000 | FTE | HIGH | 0.75% | Commission-heavy. Dealer network = faster GTM. Hire M4 only.
11 | WhatsApp Integration Specialist | M2 | ₹20,000 | ₹60,000 | Freelance | HIGH | — | ₹20K × 3 months. Gupshup API setup.
12 | Content Writer (LinkedIn + Technical) | M5 | ₹10,000 | ₹1,20,000 | Freelance | MEDIUM | — | ₹10K/month. Thought leadership + SEO.
13 | DevOps / Cloud Engineer | M4 | ₹60,000 | ₹7,20,000 | FTE | HIGH | 1.0% | AWS + CI/CD + monitoring at scale. Critical M4+.
14 | Full-Stack Engineer #3 (Fleet + IoT) | M8 | ₹65,000 | ₹7,80,000 | FTE | HIGH | 1.0% | FleetIQ + OBD-II pipeline. Required for fleet module.
15 | Data Engineer (pipelines + analytics) | M10 | ₹70,000 | ₹8,40,000 | FTE | MEDIUM | 0.75% | Dealer analytics dashboard + BI layer.
16 | Regional Sales #2 (Coimbatore) | M12 | ₹40,000 | ₹4,80,000 | FTE | MEDIUM | 0.5% | CBE dealer network expansion. Commission-heavy.
17 | CTO (external hire — post Series A) | M14 | ₹1,00,000 | ₹12,00,000 | FTE | HIGH | 2.0% | Architecture leadership at scale. Hire AFTER Series A confirmed.
18 | Product Manager | M16 | ₹70,000 | ₹8,40,000 | FTE | MEDIUM | 0.75% | OEM dashboard + enterprise features ownership.
19 | Head of Customer Success (post-100 dealers) | M18 | ₹80,000 | ₹9,60,000 | FTE | HIGH | 1.0% | Scale CS function for 100+ dealer retention.
20 | VP Sales (post Series A) | M20 | ₹1,20,000 | ₹14,40,000 | FTE | HIGH | 1.5% | National sales team build-out. Only hire at ₹15L MRR.
ANNUAL HEADCOUNT COST SUMMARY
Year 1 FTE Total |  |  | ₹7,620,000 |  | Y1 Contract/Retainer |  | ₹840,000

## 🏦 IPO Readiness
AUTOERA AI — IPO READINESS FRAMEWORK ¦ NSE SME → NSE Main Board → NASDAQ
REVENUE MILESTONES FOR IPO
Requirement | Description | Target Date | Category | Action Required
₹100Cr ARR | Minimum for NSE SME IPO consideration | Year 4–5 | Target | Build NRR >110% before this level
₹500Cr ARR | Serious NSE Main Board candidate | Year 6–7 | Strong | 3 consecutive years of growth at this level
₹1,000Cr ARR | Premium NSE or NASDAQ candidate | Year 8–9 | Elite | Profitability or clear path required
₹1,800Cr ARR | NASDAQ tier 1 listing candidate | Year 9–10 | Unicorn | Market cap target: ₹15,000–25,000Cr
GOVERNANCE REQUIREMENTS
Requirement | Description | Target Date | Category | Action Required
Independent Board Majority | Min 50% independent directors | By Year 6 | ₹500Cr ARR stage | Recruit 2 independent directors by Year 4
Audit Committee | Minimum 3 members, majority independent | By Year 5 | Pre-IPO | Chair must be financial expert (CA/CPA)
Nomination & Remuneration Committee | SEBI LODR requirement | By Year 6 | Pre-IPO | Independent chair required
Risk Management Committee | Enterprise risk framework | By Year 5 | Pre-IPO | CTO + CFO + independent director
Company Secretary (CS) | Mandatory for listed companies | By Year 5 | Pre-IPO | Hire full-time CS 2 years before filing
Whistle-blower Policy | SEBI LODR requirement | By Year 4 | Pre-IPO | Anonymous reporting mechanism from Day 1
FINANCIAL REQUIREMENTS
Requirement | Description | Target Date | Category | Action Required
3 Years Audited Financials | Big 4 or top-8 CA firm audit | By Year 7 | SEBI requirement | Switch to Big 4 audit by Year 5 minimum
Profitability or Positive Cash Flow | SEBI prefers profitability for Main Board | By Year 8 | NSE requirement | Plan path to positive EBITDA by Year 7
Clean Cap Table | No disputes, all ESOP documented | Ongoing | Investor requirement | Keep cap table updated monthly from Day 1
Related Party Transactions | Arms-length, board-approved, disclosed | Ongoing | SEBI requirement | Zero undisclosed related-party transactions ever
Revenue Quality | >80% recurring revenue for SaaS premium | By Year 6 | Valuation driver | Reduce one-time implementation revenue share
Debt Position | Low leverage for SaaS IPO | By Year 8 | Investor preference | SaaS companies IPO best with clean balance sheet
OPERATIONAL REQUIREMENTS
Requirement | Description | Target Date | Category | Action Required
SOC2 Type II Certification | Security + availability + confidentiality audit | By Year 5 | Enterprise customers | Engage auditor 12 months before target date
ISO 27001 Certification | Information security management standard | By Year 6 | OEM requirement | Aligned with DPDP Act compliance programme
DPDP Act Full Compliance | India data protection law | By Year 3 | Ongoing legal requirement | Quarterly compliance audit from Year 1
Investor Relations Function | IR team + earnings calls + analyst coverage | By Year 8 | Post-IPO | Hire VP IR 18 months before IPO filing
Public Reporting Standards | Ind AS or IFRS financial statements | By Year 7 | SEBI requirement | Switch to Ind AS from Year 5
Management Information System | Board-grade MIS for all departments | By Year 5 | Board requirement | ERP system (SAP Business One or Oracle) by Year 5
IPO PROCESS TIMELINE
Requirement | Description | Target Date | Category | Action Required
Year 8 — IPO decision made | Board approves IPO plan | Month 1–3 | Milestone | Select investment banker + legal counsel
Year 8 — Bankers appointed | SEBI-registered Category 1 Merchant Banker | Month 3–6 | Regulatory | Goldman, Kotak, Axis Capital — shortlist 3
Year 8–9 — Due diligence | Financial + legal + technical due diligence | Month 6–18 | Process | Prepare virtual data room in Year 7
Year 9 — DRHP filing | Draft Red Herring Prospectus to SEBI | Month 18–24 | Regulatory | 45–90 day SEBI review period expected
Year 9 — SEBI approval | SEBI grants no objection for IPO | Month 24–27 | Gate | Respond to SEBI observations within 30 days
Year 9 — Roadshow | Institutional investor roadshow — India + global | Month 27–29 | Execution | 2-week roadshow: Mumbai, Delhi, Singapore, London, NYC
Year 9 — Listing Day | NSE or NASDAQ listing — Day 1 trading | Month 30 | Achievement | IPO price discovery via book-building process
Post-IPO — Compliance | SEBI LODR quarterly and annual reporting | Ongoing | Permanent | Earnings calls, analyst coverage, shareholder communication